## IDEA Template
As a rule of thumb, once you have listed an idea, it is best to fill this table out right to left (i.e. start with the finsih in mind and work your way backward towards the start). Note that you can breakdown the steps between Start and Finish anyway you want. A common way is to break it down by hardware, software and assembly categories.
IDEA | START | WEEK 1 | WEEK 2 | WEEK 3 | FINISH
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In this column list things such as: - Material requirements - Software requirements - Other requirements - Cost ($) - Cost (t)
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Describe what progress should be made during week 1.
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Describe what progress should be made during week 2.
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Describe what progress should be made during week 3.
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In this column list your ideal final product, and the form it should take. - What functionality should it exhibit? - What role does the user play in the product’s functionality? - Are the materials used 3d printed, handmade or bought? - Give some thought to allowing for alternate materials and functionality if your initial design does not work out. - List other considerations, e.g. would some that is physically disabled be able to use your design? Is there a workaround? These can also be improvement made to the next iteration of your design.

## GANTT Template
| RAILROAD CROSSING GATE | [5 empty] | Project start: | [7 empty] | 2025-11-09
| Jacob Kwan | 400453713 |  |  |  |  | Display week: | [7 empty] | 0
| Nicolas Jao | 400450151
[7 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-11-03 to 2025-12-28
 | time axis 2025-11-03 to 2025-12-28
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Gather cardboard | Nicolas | 0% | 2025-11-09 | 2025-11-09 | 1
| Buy IR sensors | Nicolas | 0% | 2025-11-09 | 2025-11-09 | 1
Planning and design
| Fill in task breakdown & GANTT chart | Jacob | 0% | 2025-11-10 | 2025-11-10 | 1
| Write abstract & project description | Nicolas | 0% | 2025-11-10 | 2025-11-10 | 1
| Draw electrical schematic | Jacob | 0% | 2025-11-10 | 2025-11-10 | 1
| Figure out IR sensor connections | Jacob | 0% | 2025-11-11 | 2025-11-12 | 2
| Write pseudocode for high level logic of system | Jacob | 0% | 2025-11-11 | 2025-11-13 | 3
| Write code in C++ in Arduino IDE | Jacob | 0% | 2025-11-13 | 2025-11-15
Execution
| Build railroad crossing environment and gates | Nicolas | 0% | 2025-11-11 | 2025-11-13 | 3
| Paint/draw details on cardboard | Nicolas | 0% | 2025-11-11 | 2025-11-11 | 1
| Set up sensors and motors in position | Nicolas | 0% | 2025-11-12 | 2025-11-12 | 1
| Connect Arduino IDE to LabView | Jacob & Nicolas | 0% | 2025-11-15 | 2025-11-16 | 2
| Build HMI for system | Jacob & Nicolas | 0% | 2025-11-16 | 2025-11-16 | 1
| Convert logic in C++ to LabView block diagrams | Jacob & Nicolas | 0% | 2025-11-15 | 2025-11-17
| Connect LabView to Ubidots | Jacob & Nicolas | 0% | 2025-11-17 | 2025-11-18
| Ensure connection is working | Jacob & Nicolas | 0% | 2025-11-18 | 2025-11-18
| Set up Ubidots dashboard and data tracking | Jacob & Nicolas | 0% | 2025-11-18 | 2025-11-19
Troubleshooting
| Final inspection of system | Jacob & Nicolas | 0% | 2025-11-19 | 2025-11-24 | 6
| Troubleshooting and testing | Jacob & Nicolas | 0% | 2025-11-19 | 2025-11-24 | 6
Insert new rows ABOVE this one

## TASK BREAKDOWN Template
As a rule of thumb, a milestone represents the specific acheivement of an objective. Examples are: - Completion of design for 3d printing of parts - Completion of testing of code
STAGE | MILESTONES | TASKS | OWNER | TIME ALLOTTED | ACTUAL TIME
1 | All materials on hand | - Gather cardboard - Buy IR sensors | Nicolas | 3 days
2 | Project proposal completed | - Fill in task breakdown & GANTT chart - Write abstract and description - Draw electrical schematics | Nicolas & Jacob | 1 day
3 | Model railroad crossing constructed | - Build railroad crossing environment and gates - Paint/draw details on cardboard - Set up sensors and motors in appropriate areas | Nicolas | 1 day
4 | Simulated code generated in Arduino IDE | - Figure out how IR sensors work - Write psuedocode for high level logic of the entire system - Write the code in C++ in the Arduino IDE | Jacob | 2 days
5 | LabView code completed | - Figure out how to connect Arduino IDE to LabView - Build HMI for the system - Convert logic in C++ to LabView block diagrams | Nicolas & Jacob | 2 days
6 | Ubidots connection completed | - Connect LabView to Ubidots - Ensure connection is working - Set up Ubidots dashboard and data tracking | Nicolas & Jacob | 1 day
7 | Code is thouroughly tested | - Final inspection of system - Troubleshooting and testing | Nicolas & Jacob | 3 days

## EVENT LOG Template
EVENT | CATEGORY | FOCAL POINTS | OUTCOME

## DAILY STANDUPS Template
DATE | WORK DONE YESTERDAY | WORK TO BE DONE TODAY | ON TRACK? (Y/N)

## LESSONS LEARNED Template
WHAT WENT WELL | WHAT WENT LESS WELL | HOW COULD WE DO BETTER? | LESSONS LEARNED